## Ark1
Lofthus Frukt og saft
Timeline
Task name: | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | week 11 | week 12
Design sketching | Timeline week 12: Deadline
page layout | bar: Timeline week 3 to Timeline week 5
page construcing | bar: Timeline week 6 to Timeline week 9
Polish and testing | bar: Timeline week 10 to Timeline week 11
Agree on prefered design | bar: Timeline week 1
Complete sketchbook | bar: Timeline week 2
Sketch layout | bar: Timeline week 3 to Timeline week 4
content creation | bar: Timeline week 3 to Timeline week 7
Coding the pages | bar: Timeline week 6 to Timeline week 9
User testing and feedback | bar: Timeline week 9 to Timeline week 10
Prepare product for client | bar: Timeline week 11